## UAT Report
-- COPY THIS AREA IN THE ACK EMAIL BODY --
Orange HRM
- Project Information - |  | - Test Result - |  |  |  | - Execution Plan - |  | - Actual Execution -
Report Date. | 2021-09-27 | Status. | Tested Correctly |  |  | Start Date. | 2021-09-27 | Start Date. | 2021-09-27
Project No. |  | Completion. |  |  |  | Finish Date. | 2021-09-27 | Finish Date. | 2021-09-27
Test Cycle. |  | Total Test Case. | 69
Test Env. | Development
- Total Results To Date -
Status. | Planned #. | Planned % | Actual #. | Actual % from Result to Date.
Plan. | 69 | 100%
Tested correctly | 69 | 100% | 68 | 98.55%
Tested with non Stopping Defect |  |  | 1 | 1.449%
Tested with Showstopper |  |  | 0 | 0%
In Progress |  |  | 0 | 0%
N/A |  |  | 0 | 0%
Not Tested |  |  | 0 | 0%
- Defect / Issue Details -
Defect ID (#) | Defect Name | Description |  | PIC | Status | Detected Date | Closed Date | Type | Blocked Test Case
Bug001 | Zip able to input String | Hit Query {{url}}/api/v1/employee/:id/contact-detail |  | Arisa | Open | 2021-09-27 |  | ISSUE
No. | Type. | Scenario ID | Scenario Case |  |  |  |  | Result. | Blocked by (Defect ID)
1 | Positive | OrangeHRM001 | User Hit Query Get access token | User Hit Query Get access token | User Hit Query Get access token | User Hit Query Get access token | User Hit Query Get access token | Tested correctly
2 | Positive | OrangeHRM002 | User Hit Query Get Users | User Hit Query Get Users | User Hit Query Get Users | User Hit Query Get Users | User Hit Query Get Users | Tested correctly
3 | Positive | OrangeHRM003 | User Hit Query Get User Login | User Hit Query Get User Login | User Hit Query Get User Login | User Hit Query Get User Login | User Hit Query Get User Login | Tested correctly
4 | Negative | OrangeHRM004 | User Hit Query Get User Login but username empty | User Hit Query Get User Login but username empty | User Hit Query Get User Login but username empty | User Hit Query Get User Login but username empty | User Hit Query Get User Login but username empty | Tested correctly
5 | Negative | OrangeHRM005 | User Hit Query Get User Login but password empty | User Hit Query Get User Login but password empty | User Hit Query Get User Login but password empty | User Hit Query Get User Login but password empty | User Hit Query Get User Login but password empty | Tested correctly
6 | Negative | OrangeHRM006 | User Hit Query Get User Login but username are wrong | User Hit Query Get User Login but username are wrong | User Hit Query Get User Login but username are wrong | User Hit Query Get User Login but username are wrong | User Hit Query Get User Login but username are wrong | Tested correctly
7 | Negative | OrangeHRM007 | User Hit Query Get User Login but password are wrong | User Hit Query Get User Login but password are wrong | User Hit Query Get User Login but password are wrong | User Hit Query Get User Login but password are wrong | User Hit Query Get User Login but password are wrong | Tested correctly
8 | Negative | OrangeHRM008 | User Hit Query Get User Login but username & password are wrong | User Hit Query Get User Login but username & password are wrong | User Hit Query Get User Login but username & password are wrong | User Hit Query Get User Login but username & password are wrong | User Hit Query Get User Login but username & password are wrong | Tested correctly
9 | Positive | OrangeHRM009 | User Hit Query Punch In | User Hit Query Punch In | User Hit Query Punch In | User Hit Query Punch In | User Hit Query Punch In | Tested correctly
10 | Negative | OrangeHRM010 | User Double Hit Query Punch In | User Double Hit Query Punch In | User Double Hit Query Punch In | User Double Hit Query Punch In | User Double Hit Query Punch In | Tested correctly
11 | Positive | OrangeHRM011 | User Hit Query Punch Out | User Hit Query Punch Out | User Hit Query Punch Out | User Hit Query Punch Out | User Hit Query Punch Out | Tested correctly |  | -- COPY THIS AREA IN THE ACK EMAIL BODY --
12 | Negative | OrangeHRM012 | User Double Hit Query Punch Out | User Double Hit Query Punch Out | User Double Hit Query Punch Out | User Double Hit Query Punch Out | User Double Hit Query Punch Out | Tested correctly
13 | Negative | OrangeHRM013 | User Hit Query Punch In but datetime is empty | User Hit Query Punch In but datetime is empty | User Hit Query Punch In but datetime is empty | User Hit Query Punch In but datetime is empty | User Hit Query Punch In but datetime is empty | Tested correctly
14 | Negative | OrangeHRM014 | User Hit Query Punch In but incorrect format datetime | User Hit Query Punch In but incorrect format datetime | User Hit Query Punch In but incorrect format datetime | User Hit Query Punch In but incorrect format datetime | User Hit Query Punch In but incorrect format datetime | Tested correctly
15 | Positive | OrangeHRM015 | User Hit Query Save Employee | User Hit Query Save Employee | User Hit Query Save Employee | User Hit Query Save Employee | User Hit Query Save Employee | Tested correctly
16 | Negative | OrangeHRM016 | User Hit Query Save Employee but firstName empty | User Hit Query Save Employee but firstName empty | User Hit Query Save Employee but firstName empty | User Hit Query Save Employee but firstName empty | User Hit Query Save Employee but firstName empty | Tested correctly
17 | Negative | OrangeHRM017 | User Hit Query Save Employee but middleName empty string | User Hit Query Save Employee but middleName empty string | User Hit Query Save Employee but middleName empty string | User Hit Query Save Employee but middleName empty string | User Hit Query Save Employee but middleName empty string | Tested correctly
18 | Negative | OrangeHRM018 | User Hit Query Save Employee Detail but lastName empty string | User Hit Query Save Employee Detail but lastName empty string | User Hit Query Save Employee Detail but lastName empty string | User Hit Query Save Employee Detail but lastName empty string | User Hit Query Save Employee Detail but lastName empty string | Tested correctly
19 | Negative | OrangeHRM019 | User Hit Query Save Employee but code is empty | User Hit Query Save Employee but code is empty | User Hit Query Save Employee but code is empty | User Hit Query Save Employee but code is empty | User Hit Query Save Employee but code is empty | Tested correctly
20 | Negative | OrangeHRM020 | User Hit Query Save Employee but code more than 10 int | User Hit Query Save Employee but code more than 10 int | User Hit Query Save Employee but code more than 10 int | User Hit Query Save Employee but code more than 10 int | User Hit Query Save Employee but code more than 10 int | Tested correctly
21 | Negative | OrangeHRM021 | User Hit Query Save Employee but firstName is Integer | User Hit Query Save Employee but firstName is Integer | User Hit Query Save Employee but firstName is Integer | User Hit Query Save Employee but firstName is Integer | User Hit Query Save Employee but firstName is Integer | Tested correctly
22 | Negative | OrangeHRM022 | User Hit Query Save Employee but middleName is Integer | User Hit Query Save Employee but middleName is Integer | User Hit Query Save Employee but middleName is Integer | User Hit Query Save Employee but middleName is Integer | User Hit Query Save Employee but middleName is Integer | Tested correctly
23 | Negative | OrangeHRM023 | User Hit Query Save Employee but id is String | User Hit Query Save Employee but id is String | User Hit Query Save Employee but id is String | User Hit Query Save Employee but id is String | User Hit Query Save Employee but id is String | Tested correctly
24 | Positive | OrangeHRM024 | User Hit Query Employee Detail | User Hit Query Employee Detail | User Hit Query Employee Detail | User Hit Query Employee Detail | User Hit Query Employee Detail | Tested correctly
25 | Negative | OrangeHRM025 | User Hit Query Get Employee Detail but id not registered | User Hit Query Get Employee Detail but id not registered | User Hit Query Get Employee Detail but id not registered | User Hit Query Get Employee Detail but id not registered | User Hit Query Get Employee Detail but id not registered | Tested correctly
26 | Positive | OrangeHRM026 | User Hit Query Update Employee Detail | User Hit Query Update Employee Detail | User Hit Query Update Employee Detail | User Hit Query Update Employee Detail | User Hit Query Update Employee Detail | Tested correctly
27 | Negative | OrangeHRM027 | User Hit Query Update Employee Detail but Firstname is empty | User Hit Query Update Employee Detail but Firstname is empty | User Hit Query Update Employee Detail but Firstname is empty | User Hit Query Update Employee Detail but Firstname is empty | User Hit Query Update Employee Detail but Firstname is empty | Tested correctly
28 | Negative | OrangeHRM028 | User Hit Query Update Employee Detail but middleName empty string | User Hit Query Update Employee Detail but middleName empty string | User Hit Query Update Employee Detail but middleName empty string | User Hit Query Update Employee Detail but middleName empty string | User Hit Query Update Employee Detail but middleName empty string | Tested correctly
29 | Negative | OrangeHRM029 | User Hit Query Update Employee Detail but lastName empty string | User Hit Query Update Employee Detail but lastName empty string | User Hit Query Update Employee Detail but lastName empty string | User Hit Query Update Employee Detail but lastName empty string | User Hit Query Update Employee Detail but lastName empty string | Tested correctly
30 | Negative | OrangeHRM030 | User Hit Query Update Employee Detail but firstName is Integer | User Hit Query Update Employee Detail but firstName is Integer | User Hit Query Update Employee Detail but firstName is Integer | User Hit Query Update Employee Detail but firstName is Integer | User Hit Query Update Employee Detail but firstName is Integer | Tested correctly
31 | Negative | OrangeHRM031 | User Hit Query Update Employee Detail but middleName is Integer | User Hit Query Update Employee Detail but middleName is Integer | User Hit Query Update Employee Detail but middleName is Integer | User Hit Query Update Employee Detail but middleName is Integer | User Hit Query Update Employee Detail but middleName is Integer | Tested correctly
32 | Negative | OrangeHRM032 | User Hit Query Update Employee Detail but Invalid Marital status | User Hit Query Update Employee Detail but Invalid Marital status | User Hit Query Update Employee Detail but Invalid Marital status | User Hit Query Update Employee Detail but Invalid Marital status | User Hit Query Update Employee Detail but Invalid Marital status | Tested correctly
33 | Negative | OrangeHRM033 | User Hit Query Update Employee Detail but Invalid gender | User Hit Query Update Employee Detail but Invalid gender | User Hit Query Update Employee Detail but Invalid gender | User Hit Query Update Employee Detail but Invalid gender | User Hit Query Update Employee Detail but Invalid gender | Tested correctly
34 | Negative | OrangeHRM034 | User Hit Query Update Employee Detail but license Number Expired Date is Empty String | User Hit Query Update Employee Detail but license Number Expired Date is Empty String | User Hit Query Update Employee Detail but license Number Expired Date is Empty String | User Hit Query Update Employee Detail but license Number Expired Date is Empty String | User Hit Query Update Employee Detail but license Number Expired Date is Empty String | Tested correctly
35 | Negative | OrangeHRM035 | User Hit Query Update Employee Detail but license Number Expired Date is Invalid Format Date | User Hit Query Update Employee Detail but license Number Expired Date is Invalid Format Date | User Hit Query Update Employee Detail but license Number Expired Date is Invalid Format Date | User Hit Query Update Employee Detail but license Number Expired Date is Invalid Format Date | User Hit Query Update Employee Detail but license Number Expired Date is Invalid Format Date | Tested correctly
36 | Negative | OrangeHRM036 | User Hit Query Update Employee Detail but dob is Empty String | User Hit Query Update Employee Detail but dob is Empty String | User Hit Query Update Employee Detail but dob is Empty String | User Hit Query Update Employee Detail but dob is Empty String | User Hit Query Update Employee Detail but dob is Empty String | Tested correctly
37 | Negative | OrangeHRM037 | User Hit Query Update Employee Detail but dob is Invalid Format Date | User Hit Query Update Employee Detail but dob is Invalid Format Date | User Hit Query Update Employee Detail but dob is Invalid Format Date | User Hit Query Update Employee Detail but dob is Invalid Format Date | User Hit Query Update Employee Detail but dob is Invalid Format Date | Tested correctly
38 | Negative | OrangeHRM038 | User Hit Query Update Employee Detail but dob is String | User Hit Query Update Employee Detail but dob is String | User Hit Query Update Employee Detail but dob is String | User Hit Query Update Employee Detail but dob is String | User Hit Query Update Employee Detail but dob is String | Tested correctly
39 | Positive | OrangeHRM039 | User Hit Query Employee Search | User Hit Query Employee Search | User Hit Query Employee Search | User Hit Query Employee Search | User Hit Query Employee Search | Tested correctly
40 | Negative | OrangeHRM040 | User Hit Query Get Employee Search but name is not registered | User Hit Query Get Employee Search but name is not registered | User Hit Query Get Employee Search but name is not registered | User Hit Query Get Employee Search but name is not registered | User Hit Query Get Employee Search but name is not registered | Tested correctly
41 | Negative | OrangeHRM041 | User Hit Query Get Employee Search but code is not registered | User Hit Query Get Employee Search but code is not registered | User Hit Query Get Employee Search but code is not registered | User Hit Query Get Employee Search but code is not registered | User Hit Query Get Employee Search but code is not registered | Tested correctly
42 | Negative | OrangeHRM042 | User Hit Query Get Employee Search but dob is not registered | User Hit Query Get Employee Search but dob is not registered | User Hit Query Get Employee Search but dob is not registered | User Hit Query Get Employee Search but dob is not registered | User Hit Query Get Employee Search but dob is not registered | Tested correctly
43 | Negative | OrangeHRM043 | User Hit Query Get Employee Search but status is invalid | User Hit Query Get Employee Search but status is invalid | User Hit Query Get Employee Search but status is invalid | User Hit Query Get Employee Search but status is invalid | User Hit Query Get Employee Search but status is invalid | Tested correctly
44 | Positive | OrangeHRM044 | User Hit Query Employee Contact Detail | User Hit Query Employee Contact Detail | User Hit Query Employee Contact Detail | User Hit Query Employee Contact Detail | User Hit Query Employee Contact Detail | Tested correctly
45 | Negative | OrangeHRM045 | User Double Hit EmployeeContact Detail but id not registered | User Double Hit EmployeeContact Detail but id not registered | User Double Hit EmployeeContact Detail but id not registered | User Double Hit EmployeeContact Detail but id not registered | User Double Hit EmployeeContact Detail but id not registered | Tested correctly
46 | Positive | OrangeHRM046 | User Hit Query Save Employee Contact Detail | User Hit Query Save Employee Contact Detail | User Hit Query Save Employee Contact Detail | User Hit Query Save Employee Contact Detail | User Hit Query Save Employee Contact Detail | Tested correctly
47 | Negative | OrangeHRM047 | User Hit Query Save Employee but zip is String | User Hit Query Save Employee but zip is String | User Hit Query Save Employee but zip is String | User Hit Query Save Employee but zip is String | User Hit Query Save Employee but zip is String | Tested with non Stopping Defect | Bug001
48 | Negative | OrangeHRM048 | User Hit Query Save Employee but homeTelephone is Empty String | User Hit Query Save Employee but homeTelephone is Empty String | User Hit Query Save Employee but homeTelephone is Empty String | User Hit Query Save Employee but homeTelephone is Empty String | User Hit Query Save Employee but homeTelephone is Empty String | Tested correctly
49 | Negative | OrangeHRM049 | User Hit Query Save Employee but homeTelephone is String | User Hit Query Save Employee but homeTelephone is String | User Hit Query Save Employee but homeTelephone is String | User Hit Query Save Employee but homeTelephone is String | User Hit Query Save Employee but homeTelephone is String | Tested correctly
50 | Negative | OrangeHRM050 | User Hit Query Save Employee but homeTelephone is Special Character | User Hit Query Save Employee but homeTelephone is Special Character | User Hit Query Save Employee but homeTelephone is Special Character | User Hit Query Save Employee but homeTelephone is Special Character | User Hit Query Save Employee but homeTelephone is Special Character | Tested correctly
51 | Negative | OrangeHRM051 | User Hit Query Save Employee but homeTelephone is Combination Other Chars and Alphabetic | User Hit Query Save Employee but homeTelephone is Combination Other Chars and Alphabetic | User Hit Query Save Employee but homeTelephone is Combination Other Chars and Alphabetic | User Hit Query Save Employee but homeTelephone is Combination Other Chars and Alphabetic | User Hit Query Save Employee but homeTelephone is Combination Other Chars and Alphabetic | Tested correctly
52 | Negative | OrangeHRM052 | User Hit Query Save Employee but workTelephone is Empty String | User Hit Query Save Employee but workTelephone is Empty String | User Hit Query Save Employee but workTelephone is Empty String | User Hit Query Save Employee but workTelephone is Empty String | User Hit Query Save Employee but workTelephone is Empty String | Tested correctly
53 | Negative | OrangeHRM053 | User Hit Query Save Employee but workTelephone is String | User Hit Query Save Employee but workTelephone is String | User Hit Query Save Employee but workTelephone is String | User Hit Query Save Employee but workTelephone is String | User Hit Query Save Employee but workTelephone is String | Tested correctly
54 | Negative | OrangeHRM054 | User Hit Query Save Employee but workTelephone is Special Character | User Hit Query Save Employee but workTelephone is Special Character | User Hit Query Save Employee but workTelephone is Special Character | User Hit Query Save Employee but workTelephone is Special Character | User Hit Query Save Employee but workTelephone is Special Character | Tested correctly
55 | Negative | OrangeHRM055 | User Hit Query Save Employee but workTelephone is Combination Other Chars and Alphabetic | User Hit Query Save Employee but workTelephone is Combination Other Chars and Alphabetic | User Hit Query Save Employee but workTelephone is Combination Other Chars and Alphabetic | User Hit Query Save Employee but workTelephone is Combination Other Chars and Alphabetic | User Hit Query Save Employee but workTelephone is Combination Other Chars and Alphabetic | Tested correctly
56 | Negative | OrangeHRM056 | User Hit Query Save Employee but mobile is Empty String | User Hit Query Save Employee but mobile is Empty String | User Hit Query Save Employee but mobile is Empty String | User Hit Query Save Employee but mobile is Empty String | User Hit Query Save Employee but mobile is Empty String | Tested correctly
57 | Negative | OrangeHRM057 | User Hit Query Save Employee but mobile is String | User Hit Query Save Employee but mobile is String | User Hit Query Save Employee but mobile is String | User Hit Query Save Employee but mobile is String | User Hit Query Save Employee but mobile is String | Tested correctly
58 | Negative | OrangeHRM058 | User Hit Query Save Employee but mobile is Special Character | User Hit Query Save Employee but mobile is Special Character | User Hit Query Save Employee but mobile is Special Character | User Hit Query Save Employee but mobile is Special Character | User Hit Query Save Employee but mobile is Special Character | Tested correctly
59 | Negative | OrangeHRM059 | User Hit Query Save Employee but mobile is Combination Other Chars and Alphabetic | User Hit Query Save Employee but mobile is Combination Other Chars and Alphabetic | User Hit Query Save Employee but mobile is Combination Other Chars and Alphabetic | User Hit Query Save Employee but mobile is Combination Other Chars and Alphabetic | User Hit Query Save Employee but mobile is Combination Other Chars and Alphabetic | Tested correctly
60 | Negative | OrangeHRM060 | User Hit Query Save Employee but workEmail is Empty String | User Hit Query Save Employee but workEmail is Empty String | User Hit Query Save Employee but workEmail is Empty String | User Hit Query Save Employee but workEmail is Empty String | User Hit Query Save Employee but workEmail is Empty String | Tested correctly
61 | Negative | OrangeHRM061 | User Hit Query Save Employee but workEmail is Invalid FormatEmail | User Hit Query Save Employee but workEmail is Invalid FormatEmail | User Hit Query Save Employee but workEmail is Invalid FormatEmail | User Hit Query Save Employee but workEmail is Invalid FormatEmail | User Hit Query Save Employee but workEmail is Invalid FormatEmail | Tested correctly
62 | Negative | OrangeHRM062 | User Hit Query Save Employee but otherEmail is Empty string | User Hit Query Save Employee but otherEmail is Empty string | User Hit Query Save Employee but otherEmail is Empty string | User Hit Query Save Employee but otherEmail is Empty string | User Hit Query Save Employee but otherEmail is Empty string | Tested correctly
63 | Negative | OrangeHRM063 | User Hit Query Save Employee but otherEmail is Invalid FormatEmail | User Hit Query Save Employee but otherEmail is Invalid FormatEmail | User Hit Query Save Employee but otherEmail is Invalid FormatEmail | User Hit Query Save Employee but otherEmail is Invalid FormatEmail | User Hit Query Save Employee but otherEmail is Invalid FormatEmail | Tested correctly
64 | Negative | OrangeHRM064 | User Hit Query Save Employee but workEmail and otherEmail is same | User Hit Query Save Employee but workEmail and otherEmail is same | User Hit Query Save Employee but workEmail and otherEmail is same | User Hit Query Save Employee but workEmail and otherEmail is same | User Hit Query Save Employee but workEmail and otherEmail is same | Tested correctly
65 | Positive | OrangeHRM065 | User Hit Query Update Employee Contact Detail | User Hit Query Update Employee Contact Detail | User Hit Query Update Employee Contact Detail | User Hit Query Update Employee Contact Detail | User Hit Query Update Employee Contact Detail | Tested correctly
66 | Positive | OrangeHRM066 | User Hit Query Save Employee Dependent | User Hit Query Save Employee Dependent | User Hit Query Save Employee Dependent | User Hit Query Save Employee Dependent | User Hit Query Save Employee Dependent | Tested correctly
67 | Positive | OrangeHRM067 | User Hit Query Get Employee Dependent | User Hit Query Get Employee Dependent | User Hit Query Get Employee Dependent | User Hit Query Get Employee Dependent | User Hit Query Get Employee Dependent | Tested correctly
68 | Positive | OrangeHRM068 | User Hit Query Delete Employee Dependent | User Hit Query Delete Employee Dependent | User Hit Query Delete Employee Dependent | User Hit Query Delete Employee Dependent | User Hit Query Delete Employee Dependent | Tested correctly
69 | Positive | OrangeHRM069 | User Hit Query Terminate Employee | User Hit Query Terminate Employee | User Hit Query Terminate Employee | User Hit Query Terminate Employee | User Hit Query Terminate Employee | Tested correctly

## UAT Scenario
No | Scenario ID | Scenario Cases | Feature | Involved System or Application | Scenario Type | Planned Date | Execution Date | Status | Tester | Notes
1 | OrangeHRM001 | User Hit Query Get access token | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
2 | OrangeHRM002 | User Hit Query Get Users | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
3 | OrangeHRM003 | User Hit Query Get User Login | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
4 | OrangeHRM004 | User Hit Query Get User Login but username empty | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
5 | OrangeHRM005 | User Hit Query Get User Login but password empty | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
6 | OrangeHRM006 | User Hit Query Get User Login but username are wrong | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
7 | OrangeHRM007 | User Hit Query Get User Login but password are wrong | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
8 | OrangeHRM008 | User Hit Query Get User Login but username & password are wrong | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
9 | OrangeHRM009 | User Hit Query Punch In | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
10 | OrangeHRM010 | User Double Hit Query Punch In | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
11 | OrangeHRM011 | User Hit Query Punch Out | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
12 | OrangeHRM012 | User Double Hit Query Punch Out | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
13 | OrangeHRM013 | User Hit Query Punch In but datetime is empty | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
14 | OrangeHRM014 | User Hit Query Punch In but incorrect format datetime | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
15 | OrangeHRM015 | User Hit Query Save Employee | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
16 | OrangeHRM016 | User Hit Query Save Employee but firstName empty | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
17 | OrangeHRM017 | User Hit Query Save Employee but middleName empty string | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
18 | OrangeHRM018 | User Hit Query Save Employee Detail but lastName empty string | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
19 | OrangeHRM019 | User Hit Query Save Employee but code is empty | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
20 | OrangeHRM020 | User Hit Query Save Employee but code more than 10 int | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
21 | OrangeHRM021 | User Hit Query Save Employee but firstName is Integer | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
22 | OrangeHRM022 | User Hit Query Save Employee but middleName is Integer | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
23 | OrangeHRM023 | User Hit Query Save Employee but id is String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
24 | OrangeHRM024 | User Hit Query Employee Detail | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
25 | OrangeHRM025 | User Hit Query Get Employee Detail but id not registered | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
26 | OrangeHRM026 | User Hit Query Update Employee Detail | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
27 | OrangeHRM027 | User Hit Query Update Employee Detail but Firstname is empty | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
28 | OrangeHRM028 | User Hit Query Update Employee Detail but middleName empty string | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
29 | OrangeHRM029 | User Hit Query Update Employee Detail but lastName empty string | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
30 | OrangeHRM030 | User Hit Query Update Employee Detail but firstName is Integer | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
31 | OrangeHRM031 | User Hit Query Update Employee Detail but middleName is Integer | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
32 | OrangeHRM032 | User Hit Query Update Employee Detail but Invalid Marital status | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
33 | OrangeHRM033 | User Hit Query Update Employee Detail but Invalid gender | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
34 | OrangeHRM034 | User Hit Query Update Employee Detail but license Number Expired Date is Empty String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
35 | OrangeHRM035 | User Hit Query Update Employee Detail but license Number Expired Date is Invalid Format Date | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
36 | OrangeHRM036 | User Hit Query Update Employee Detail but dob is Empty String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
37 | OrangeHRM037 | User Hit Query Update Employee Detail but dob is Invalid Format Date | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
38 | OrangeHRM038 | User Hit Query Update Employee Detail but dob is String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
39 | OrangeHRM039 | User Hit Query Employee Search | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
40 | OrangeHRM040 | User Hit Query Get Employee Search but name is not registered | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
41 | OrangeHRM041 | User Hit Query Get Employee Search but code is not registered | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
42 | OrangeHRM042 | User Hit Query Get Employee Search but dob is not registered | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
43 | OrangeHRM043 | User Hit Query Get Employee Search but status is invalid | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
44 | OrangeHRM044 | User Hit Query Employee Contact Detail | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
45 | OrangeHRM045 | User Double Hit EmployeeContact Detail but id not registered | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
46 | OrangeHRM046 | User Hit Query Save Employee Contact Detail | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
47 | OrangeHRM047 | User Hit Query Save Employee but zip is String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
48 | OrangeHRM048 | User Hit Query Save Employee but homeTelephone is Empty String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
49 | OrangeHRM049 | User Hit Query Save Employee but homeTelephone is String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
50 | OrangeHRM050 | User Hit Query Save Employee but homeTelephone is Special Character | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
51 | OrangeHRM051 | User Hit Query Save Employee but homeTelephone is Combination Other Chars and Alphabetic | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
52 | OrangeHRM052 | User Hit Query Save Employee but workTelephone is Empty String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
53 | OrangeHRM053 | User Hit Query Save Employee but workTelephone is String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
54 | OrangeHRM054 | User Hit Query Save Employee but workTelephone is Special Character | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
55 | OrangeHRM055 | User Hit Query Save Employee but workTelephone is Combination Other Chars and Alphabetic | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
56 | OrangeHRM056 | User Hit Query Save Employee but mobile is Empty String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
57 | OrangeHRM057 | User Hit Query Save Employee but mobile is String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
58 | OrangeHRM058 | User Hit Query Save Employee but mobile is Special Character | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
59 | OrangeHRM059 | User Hit Query Save Employee but mobile is Combination Other Chars and Alphabetic | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
60 | OrangeHRM060 | User Hit Query Save Employee but workEmail is Empty String | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
61 | OrangeHRM061 | User Hit Query Save Employee but workEmail is Invalid FormatEmail | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
62 | OrangeHRM062 | User Hit Query Save Employee but otherEmail is Empty string | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
63 | OrangeHRM063 | User Hit Query Save Employee but otherEmail is Invalid FormatEmail | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
64 | OrangeHRM064 | User Hit Query Save Employee but workEmail and otherEmail is same | Negative | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
65 | OrangeHRM065 | User Hit Query Update Employee Contact Detail | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
66 | OrangeHRM066 | User Hit Query Save Employee Dependent | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
67 | OrangeHRM067 | User Hit Query Get Employee Dependent | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
68 | OrangeHRM068 | User Hit Query Delete Employee Dependent | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty
69 | OrangeHRM069 | User Hit Query Terminate Employee | Positive | OrangeHRM | Positive | 27-09-2021 | 27-09-2021 | Tested Correctly | Arisa Hazriaty

## Scenario Cases
Test Case ID | Feature | Precondition | Positive/Negative | Scenario Name | Test Case Objective | Test Step | Expected Behaviour | Actual Behaviour | Result | Automated | Bug-ID
OrangeHRM001 | Get Access Token | User have client_id & client_secret | Positive | User Hit Query Get access token | User should Get Access Token to access Orang HRM | client_id:{{client_id}} Client_secret:{{client_secret}} grant_type:{{grant_type}} | Verify Responses displayed: "access_token": "{{access_token}}", "expires_in": {{expires_in}} "token_type": {{token_type}}, "scope": "{{scope}} | Responses already displayed correctly: "access_token": "{{access_token}}", "expires_in": {{expires_in}} "token_type": {{token_type}}, "scope": "{{scope}} | Passed | Yes
OrangeHRM002 | Admin | User have token | Positive | User Hit Query Get Users | User able to view another user | Hit Query {{url}}/api/v1/user | Verify Responses displayed: "userName": "{{userName}}", "userRole": "{{userRole}}", "status": "{{status}}", "employeeName": "{{employeeName}} "employeeId": "{{employeeId}}" | Responses already displayed correctly: "userName": "{{userName}}", "userRole": "{{userRole}}", "status": "{{status}}", "employeeName": "{{employeeName}} "employeeId": "{{employeeId}}" | Passed | Yes
OrangeHRM003 | Admin | User have token | Positive | User Hit Query Get User Login but password are wrong | User able to login | username:{{username}} password:{{password}} | Verify Responses displayed: "login": true, "user": { "userName": "{{userName}}", "userRole": "{{userRole}}", "status": "{{status}}", "employeeName": "{{employeeName}}", "employeeId": "{{employeeId}}" | Responses already displayed correctly: "login": true, "user": { "userName": "{{userName}}", "userRole": "{{userRole}}", "status": "{{status}}", "employeeName": "{{employeeName}}", "employeeId": "{{employeeId}}" | Passed | Yes
OrangeHRM004 | Admin | User have token | Negative | User Hit Query Get User Login but username empty | Username must not be empty | Username:”” password:{{password}} | Verify Responses displayed: "error": { "status": "202", "text": "username must not be empty" } | Responses already displayed correctly: "error": { "status": "202", "text": "username must not be empty" } | Passed | No
OrangeHRM005 | Admin | User have token | Negative | User Hit Query Get User Login but password empty | Password must not be empty | username:{{username}} Password: | Verify Responses displayed: "error": { "status": "202", "text": "password must not be empty" } | Responses already displayed correctly: "error": { "status": "202", "text": "password must not be empty" } | Passed | No
OrangeHRM006 | Admin | User have token | Negative | User Hit Query Get User Login but username are wrong | User should input correct username and password | username:wrongusername password:{{password}} | Verify Responses displayed: "error": { "status": "202", "text": "Credentials Are Wrong Please Try Again" } | Response already displayed correctly: "error": { "status": "202", "text": "Credentials Are Wrong Please Try Again" } | Passed | No
OrangeHRM007 | Admin | User have token | Negative | User Hit Query Get User Login but password are wrong | User should input correct username and password | username:{{username}} password:wrongpassword | Verify Responses displayed: "error": { "status": "202", "text": "Credentials Are Wrong Please Try Again" } | Response already displayed correctly: "error": { "status": "202", "text": "Credentials Are Wrong Please Try Again" } | Passed | No
OrangeHRM008 | Admin | User have token | Negative | User Hit Query Get User Login but username & password are wrong | User should input correct username and password | username:wrongusername password:wrongpassword | Verify Responses displayed: "error": { "status": "202", "text": "Credentials Are Wrong Please Try Again" } | Response already displayed correctly: "error": { "status": "202", "text": "Credentials Are Wrong Please Try Again" } | Passed | No
OrangeHRM009 | Attendance | User have token | Positive | User Hit Query Punch In | User able to Punch In | id:{{employeeid}} timezone:{{timezone}} note:{{note}} datetime:{{datetimePunchIn}} | Verify Responses displayed: "success": "{{successMessage}}", "id": "{{id}}" | Responses already displayed correctly: "success": "{{successMessage}}", "id": "{{id}}" | Passed | Yes
OrangeHRM010 | Attendance | User have token | Negative | User Double Hit Query Punch In | User cannot Punch In if already Punch In | Double hit {{url}}/api/v1/employee/:employeeid/punch-in | Verify Responses displayed: "error": { "status": "202", "text": "Cannot Proceed Punch In Employee Already Punched In" } | Responses already displayed correctly: "error": { "status": "202", "text": "Cannot Proceed Punch In Employee Already Punched In" } | Passed | No
OrangeHRM011 | Attendance | User have token | Positive | User Hit Query Punch Out | User able to Punch Out | id:{{employeeid}} timezone:{{timezone}} note:{{note}} datetime:{{datetimePunchOut}} | Verify Responses displayed: "success": "{{successMessage}}", "id": "{{id}}" | Responses already displayed correctly: "success": "{{successMessage}}", "id": "{{id}}" | Passed | Yes
OrangeHRM012 | Attendance | User have token | Negative | User Double Hit Query Punch Out | User cannot Punch Out if already Punch Out | Doublr Hit {{url}}/api/v1/employee/:employeeid/punch-out | Verify Responses displayed: "error": { "status": "202", "text": "Cannot Proceed Punch Out Employee Already Punched Out" } | Responses already displayed correctly: "error": { "status": "202", "text": "Cannot Proceed Punch Out Employee Already Punched Out" } | Passed | No
OrangeHRM013 | Attendance | User have token | Negative | User Hit Query Punch In but datetime is empty | Date must be a valid date | id:{{employeeid}} timezone:{{timezone}} note:{{note}} Datetime: | Verify Responses displayed: "error": { "status": "202", "text": "datetime must be a valid date. Sample format: \"2005-12-30 01:02\"" } | Response already displayed correctly: "error": { "status": "202", "text": "datetime must be a valid date. Sample format: \"2005-12-30 01:02\"" } | Passed | No
OrangeHRM014 | Attendance | User have token | Negative | User Hit Query Punch In but incorrect format datetime | Date must be a valid date | id:{{employeeid}} timezone:{{timezone}} note:{{note}} datetime:datetime | Verify Responses displayed: "error": { "status": "202", "text": "datetime must be a valid date. Sample format: \"2005-12-30 01:02\"" } | Response already displayed correctly: "error": { "status": "202", "text": "datetime must be a valid date. Sample format: \"2005-12-30 01:02\"" } | Passed | No
OrangeHRM015 | Employee | User have token | Positive | User Hit Query Save Employee | User able to Save Employee | "firstName": "{{firstName}}", "middleName":"{{middleName}}", "lastName":"{{lastName}}", "code":"{{randomCodeEmployee}}" | Verify Responses displayed: "success": "{{successMessage}}", "id": "{{id}}" | Responses already displayed correctly: "success": "{{successMessage}}", "id": "{{id}}" | Passed | Yes
OrangeHRM016 | Employee | User have token | Negative | User Hit Query Save Employee but firstName empty | Firstname should not be empty | "firstName": "","middleName":"{{middleName}}","lastName":"{{lastName}}","code":"{{randomCodeEmployee}}" | Verify Responses displayed: "error": { "status": "202", "text": "firstName must not be empty" } | Responses already displayed correctly: "error": { "status": "202", "text": "firstName must not be empty" } | Passed | No
OrangeHRM017 | Employee | User have token | Negative | User Hit Query Save Employee but middleName empty string | middleName must have a length between 1 and 30 | "firstName": "{{firstName}}", "middleName":"", "lastName":"{{lastName}}", "code":"{{randomCodeEmployee}}" | Verify Responses displayed: "error": { "status": "202", "text": "middleName must have a length between 1 and 30" } | Responses already displayed correctly: "error": { "status": "202", "text": "middleName must have a length between 1 and 30" } | Passed | No
OrangeHRM018 | Employee | User have token | Negative | User Hit Query Save Employee Detail but lastName empty string | lastName must not be empty | "firstName": "{{firstName}}","middleName":"{{middleName}}","lastName":"","code":"{{randomCodeEmployee}}" | Verify Responses displayed: "error": { "status": "202", "text": "lastName must not be empty" } | Responses already displayed correctly: "error": { "status": "202", "text": "lastName must not be empty" } | Passed | No
OrangeHRM019 | Employee | User have token | Negative | User Hit Query Save Employee but code is empty | code must have a length between 1 and 10 | "firstName": "{{firstName}}","middleName":"{{middleName}}","lastName":"{{lastName}}","code":"" | Verify Responses displayed: "error": { "status": "202", "text": "code must have a length between 1 and 10" } | Responses already displayed correctly: "error": { "status": "202", "text": "code must have a length between 1 and 10" } | Passed | No
OrangeHRM020 | Employee | User have token | Negative | User Hit Query Save Employee but code more than 10 int | code must have a length between 1 and 10 | "firstName": "{{firstName}}","middleName":"{{middleName}}","lastName":"{{lastName}}","code":"11111111111" | Verify Responses displayed: "error": { "status": "202", "text": "code must have a length between 1 and 10" } | Responses already displayed correctly: "error": { "status": "202", "text": "code must have a length between 1 and 10" } | Passed | No
OrangeHRM021 | Employee | User have token | Negative | User Hit Query Save Employee but firstName is Integer | firstName must be a string | { "firstName": 12345, "middleName":"{{middleName}}", "lastName":"{{lastName}}", "code":"{{randomCodeEmployee}}" } | Verify Responses displayed: "error": { "status": "202", "text": "firstName must be a string" } | Responses already displayed correctly: "error": { "status": "202", "text": "firstName must be a string" } | Passed | No
OrangeHRM022 | Employee | User have token | Negative | User Hit Query Save Employee but middleName is Integer | lastName must be a string | { "firstName":"{{firstName}}", "middleName":12345, "lastName":"{{lastName}}", "code":"{{randomCodeEmployee}}" } | Verify Responses displayed: "error": { "status": "202", "text": "middleName must be a string" } | Responses already displayed correctly: "error": { "status": "202", "text": "middleName must be a string" } | Passed | No
OrangeHRM023 | Employee | User have token | Negative | User Hit Query Save Employee but id is String | code must be a string | "firstName": "{{firstName}}", "middleName":"{{middleName}}", "lastName":"{{lastName}}", "code":{{randomCodeEmployee}} | Verify Responses displayed: "error": { "status": "202", "text": "code must be a string" } | Responses already displayed correctly: "error": { "status": "202", "text": "code must be a string" } | Passed | No
OrangeHRM024 | Employee | User have token | Positive | User Hit Query Employee Detail | User able to view Employee Detail | Hit Query {{url}}/api/v1/employee/:id | Verify Responses displayed: "firstName": "{{firstName}}", "middleName": "{{middleName}}", "lastName": "{{lastName}}", "code": "{{code}}", "employeeId": "{{employeeId}}", "fullName": "{{fullName}}", "status": "{{status}}", "dob": "{{dob}}", "driversLicenseNumber": "{{driversLicenseNumber}}", "licenseExpiryDate": "{{licenseExpiryDate}}", "maritalStatus": "{{maritalStatus}}", "gender": "{{gender}}", "otherId": "{{otherId}}", "nationality": "{{nationality}}", "unit": "{{unit}}", "jobTitle": "{{jobTitle}}", "supervisor": "{{supervisor}}" | Responser already displayed correctly: "firstName": "{{firstName}}", "middleName": "{{middleName}}", "lastName": "{{lastName}}", "code": "{{code}}", "employeeId": "{{employeeId}}", "fullName": "{{fullName}}", "status": "{{status}}", "dob": "{{dob}}", "driversLicenseNumber": "{{driversLicenseNumber}}", "licenseExpiryDate": "{{licenseExpiryDate}}", "maritalStatus": "{{maritalStatus}}", "gender": "{{gender}}", "otherId": "{{otherId}}", "nationality": "{{nationality}}", "unit": "{{unit}}", "jobTitle": "{{jobTitle}}", "supervisor": "{{supervisor}}" | Passed | Yes
OrangeHRM025 | Employee | User have token | Negative | User Hit Query Get Employee Detail but id not registered | User able to see error Employee not found | Hit Query {{url}}/api/v1/employee/:99999 | Verify Responses displayed: "error": { "status": "404", "text": "Employee Not Found" } | Responses already displayed correctly: "error": { "status": "404", "text": "Employee Not Found" } | Passed | No
OrangeHRM026 | Employee | User have token | Positive | User Hit Query Update Employee Detail | User able to update Employee Detail | "id":"{{newemployeeid}}", "firstName": "{{firstName}}", "middleName": "{{middleName}}", "lastName": "{{lastName}}", "code": "{{randomCodeEmployee}}", "dob": "{{dob}}", "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "{{licenseNumberExpDate}}", "maritalStatus": "{{maritalStatus}}", "gender": "{{gender}}", "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "success": "{{successMessage}}", | Verify Responses displayed: "success": "{{successMessage}}", | Passed | Yes
OrangeHRM027 | Employee | User have token | Negative | User Hit Query Update Employee Detail but Firstname is empty | Firstname should not be empty | "id":"{{newemployeeid}}", "firstName": "", "middleName": "{{middleName}}", "lastName": "{{lastName}}", "code": "{{randomCodeEmployee}}", "dob": "{{dob}}", "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "{{licenseNumberExpDate}}", "maritalStatus": "{{maritalStatus}}", "gender": "{{gender}}", "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "firstName must not be empty" } | Responses already displayed correctly: "error": { "status": "202", "text": "firstName must not be empty" } | Passed | No
OrangeHRM028 | Employee | User have token | Negative | User Hit Query Update Employee Detail but middleName empty string | middleName must have a length between 1 and 30 | "id":"{{newemployeeid}}", "firstName": "{{firstName}}", "middleName": "", "lastName": "{{lastName}}", "code": "{{randomCodeEmployee}}", "dob": "{{dob}}", "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "{{licenseNumberExpDate}}", "maritalStatus": "{{maritalStatus}}", "gender": "{{gender}}", "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "middleName must have a length between 1 and 30" } | Responses already displayed correctly: "error": { "status": "202", "text": "middleName must have a length between 1 and 30" } | Passed | No
OrangeHRM029 | Employee | User have token | Negative | User Hit Query Update Employee Detail but lastName empty string | lastName must not be empty | "id":"{{newemployeeid}}", "firstName": "{{firstName}}", "middleName": "{{middleName}}", "lastName": "", "code": "{{randomCodeEmployee}}", "dob": "{{dob}}", "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "{{licenseNumberExpDate}}", "maritalStatus": "{{maritalStatus}}", "gender": "{{gender}}", "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "lastName must not be empty" } | Responses already displayed correctly: "error": { "status": "202", "text": "lastName must not be empty" } | Passed | No
OrangeHRM030 | Employee | User have token | Negative | User Hit Query Update Employee Detail but firstName is Integer | firstName must be a string | "id":"{{newemployeeid}}", "firstName": 12345, "middleName": "{{middleName}}", "lastName": “{{lastName}}”, "code": "{{randomCodeEmployee}}", "dob": "{{dob}}", "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "{{licenseNumberExpDate}}", "maritalStatus": "{{maritalStatus}}", "gender": "{{gender}}", "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "firstName must be a string" } | Responses already displayed correctly: "error": { "status": "202", "text": "firstName must be a string" } | Passed | No
OrangeHRM031 | Employee | User have token | Negative | User Hit Query Update Employee Detail but middleName is Integer | middleName must be a string | "id":"{{newemployeeid}}", "firstName": “{{firstName}}”, "middleName": 12345, "lastName": “{{lastName}}”, "code": "{{randomCodeEmployee}}", "dob": "{{dob}}", "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "{{licenseNumberExpDate}}", "maritalStatus": "{{maritalStatus}}", "gender": "{{gender}}", "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "middleName must be a string" } | Responses already displayed correctly: "error": { "status": "202", "text": "middleName must be a string" } | Passed | No
OrangeHRM032 | Employee | User have token | Negative | User Hit Query Update Employee Detail but Invalid Marital status | Mariltal Status should valid data | "id":"{{newemployeeid}}", "firstName": “{{firstName}}”, "middleName": {{middleName}}, "lastName": “{{lastName}}”, "code": "{{randomCodeEmployee}}", "dob": "{{dob}}", "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "{{licenseNumberExpDate}}", "maritalStatus": "testing”, "gender": "{{gender}}", "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "Invalid Marital Status" } | Responses already displayed correctly: "error": { "status": "202", "text": "Invalid Marital Status" } | Passed | No
OrangeHRM033 | Employee | User have token | Negative | User Hit Query Update Employee Detail but Invalid gender | Gender should valid data | "id":"{{newemployeeid}}", "firstName": “{{firstName}}”, "middleName": {{middleName}}, "lastName": “{{lastName}}”, "code": "{{randomCodeEmployee}}", "dob": "{{dob}}", "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "{{licenseNumberExpDate}}", "maritalStatus": "{{maritalstatus}}”, "gender": "testing", "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "Updating Failed" } | Responses already displayed correctly: "error": { "status": "202", "text": "Updating Failed" } | Passed | No
OrangeHRM034 | Employee | User have token | Negative | User Hit Query Update Employee Detail but license Number Expired Date is Empty String | License Number Expired date must a valid data | "id":"{{newemployeeid}}", "firstName": “{{firstName}}”, "middleName": {{middleName}}, "lastName": “{{lastName}}”, "code": "{{randomCodeEmployee}}", "dob": "{{dob}}", "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "", "maritalStatus": "{{maritalstatus}}”, "gender": "testing", "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "licenseNumberExpDate must be a valid date. Sample format: \"2005-12-30\"" } | Responses already displayed correctly: "error": { "status": "202", "text": "licenseNumberExpDate must be a valid date. Sample format: \"2005-12-30\"" } | Passed | No
OrangeHRM035 | Employee | User have token | Negative | User Hit Query Update Employee Detail but license Number Expired Date is Invalid Format Date | License Number Expired date must a valid data | "id":"{{newemployeeid}}", "firstName": “{{firstName}}”, "middleName": {{middleName}}, "lastName": “{{lastName}}”, "code": "{{randomCodeEmployee}}", "dob": "{{dob}}", "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "testing", "maritalStatus": "{{maritalstatus}}”, "gender": "{{gender}}”, "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "licenseNumberExpDate must be a valid date. Sample format: \"2005-12-30\"" } | Responses already displayed correctly: "error": { "status": "202", "text": "licenseNumberExpDate must be a valid date. Sample format: \"2005-12-30\"" } | Passed | No
OrangeHRM036 | Employee | User have token | Negative | User Hit Query Update Employee Detail but dob is Empty String | Dob must be a valid date | "id":"{{newemployeeid}}", "firstName": “{{firstName}}”, "middleName": {{middleName}}, "lastName": “{{lastName}}”, "code": "{{randomCodeEmployee}}", "dob": "", "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "{{licenseNumberExpDate}}”, "maritalStatus": "{{maritalstatus}}”, "gender": "{{gender}}”, "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "licenseNumberExpDate must be a valid date. Sample format: \"2005-12-30\"" } | Responses already displayed correctly: "error": { "status": "202", "text": "licenseNumberExpDate must be a valid date. Sample format: \"2005-12-30\"" } | Passed | No
OrangeHRM037 | Employee | User have token | Negative | User Hit Query Update Employee Detail but dob is Invalid Format Date | Dob must be a valid date | "id":"{{newemployeeid}}", "firstName": “{{firstName}}”, "middleName": {{middleName}}, "lastName": “{{lastName}}”, "code": "{{randomCodeEmployee}}", "dob": 2012-01, "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "{{licenseNumberExpDate}}”, "maritalStatus": "{{maritalstatus}}”, "gender": "{{gender}}”, "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "licenseNumberExpDate must be a valid date. Sample format: \"2005-12-30\"" } | Responses already displayed correctly: "error": { "status": "202", "text": "licenseNumberExpDate must be a valid date. Sample format: \"2005-12-30\"" } | Passed | No
OrangeHRM038 | Employee | User have token | Negative | User Hit Query Update Employee Detail but dob is String | Dob must be a valid date | "id":"{{newemployeeid}}", "firstName": “{{firstName}}”, "middleName": {{middleName}}, "lastName": “{{lastName}}”, "code": "{{randomCodeEmployee}}", "dob": “testing”, "licenseNumber": "{{licenseNumber}}", "licenseNumberExpDate": "{{licenseNumberExpDate}}”, "maritalStatus": "{{maritalstatus}}”, "gender": "{{gender}}”, "otherId": "{{otherId}}", "nationality": "{{nationality}}" | Verify Responses displayed: "error": { "status": "202", "text": "licenseNumberExpDate must be a valid date. Sample format: \"2005-12-30\"" } | Verify Responses displayed: "error": { "status": "202", "text": "licenseNumberExpDate must be a valid date. Sample format: \"2005-12-30\"" } | Passed | No
OrangeHRM039 | Employee | User have token | Positive | User Hit Query Employee Search | User able to search Employee | Hit Query {{url}}/api/v1/employee/search?name={{Name}}&code={{randomCodeEmployee}}&dob={{dob}} | Verify Responses displayed: "firstName": "{{firstName}}", "middleName": "{{middleName}}", "lastName": "{{lastName}}", "code": "{{code}}", "employeeId": "{{employeeId}}", "fullName": "{{fullName}}", "status": "{{status}}", "dob": "{{dob}}", "driversLicenseNumber": "{{driversLicenseNumber}}", "licenseExpiryDate": "{{licenseExpiryDate}}", "maritalStatus": "{{maritalStatus}}", "gender": "{{gender}}", "otherId": "{{otherId}}", "nationality": "{{nationality}}", "unit": "{{unit}}", "jobTitle": "{{jobTitle}}", "supervisor": "{{supervisor}}" | Responses already displayed correctly: "firstName": "{{firstName}}", "middleName": "{{middleName}}", "lastName": "{{lastName}}", "code": "{{code}}", "employeeId": "{{employeeId}}", "fullName": "{{fullName}}", "status": "{{status}}", "dob": "{{dob}}", "driversLicenseNumber": "{{driversLicenseNumber}}", "licenseExpiryDate": "{{licenseExpiryDate}}", "maritalStatus": "{{maritalStatus}}", "gender": "{{gender}}", "otherId": "{{otherId}}", "nationality": "{{nationality}}", "unit": "{{unit}}", "jobTitle": "{{jobTitle}}", "supervisor": "{{supervisor}}" | Passed | Yes
OrangeHRM040 | Employee | User have token | Negative | User Hit Query Get Employee Search but name is not registered | User able to see error Employee not found | {{url}}/api/v1/employee/search?name={{Name1}}&code={{randomCodeEmployee}}&dob={{dob}} | Verify Responses displayed: "error": { "status": "404", "text": "Employee Not Found" } | Responses already displayed correctly: "error": { "status": "404", "text": "Employee Not Found" } | Passed | No
OrangeHRM041 | Employee | User have token | Negative | User Hit Query Get Employee Search but code is not registered | User able to see error Employee not found | {{url}}/api/v1/employee/search?name={{Name}}&code={{4123413241}}&dob={{dob}} | Verify Responses displayed: "error": { "status": "404", "text": "Employee Not Found" } | Responses already displayed correctly: "error": { "status": "404", "text": "Employee Not Found" } | Passed | No
OrangeHRM042 | Employee | User have token | Negative | User Hit Query Get Employee Search but dob is not registered | User able to see error Employee not found | {{url}}/api/v1/employee/search?name={{Name}}&code={{randomCodeEmployee}}&dob={{dob}} | Verify Responses displayed: "error": { "status": "404", "text": "Employee Not Found" } | Responses already displayed correctly: "error": { "status": "404", "text": "Employee Not Found" } | Passed | No
OrangeHRM043 | Employee | User have token | Negative | User Hit Query Get Employee Search but status is invalid | User able to see error Employee not found | {{url}}/api/v1/employee/search?status=not null | Verify Responses displayed: "error": { "status": "202", "text": "Invalid Status" } | Responses already displayed correctly: "error": { "status": "202", "text": "Invalid Status" } | Passed | No
OrangeHRM044 | Employee | User have token | Positive | User Hit Query Employee Contact Detail | User able to see Employee Contact Detail | Hit Query {{url}}/api/v1/employee/:id/contact-detail | Verify Responses displayed: "data": { "id": "{{id}}", "code": "{{code}}", "fullName": "{{fullName}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "county": "{{county}}", "homeTelephone": "{{homeTelephone}}", "workTelephone": "{{workTelephone}}", "mobile": "{{mobile}}", "workEmail": "{{workEmail}}", "otherEmail": "{{otherEmail}}" } | Responses already displayed correctly: "data": { "id": "{{id}}", "code": "{{code}}", "fullName": "{{fullName}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "county": "{{county}}", "homeTelephone": "{{homeTelephone}}", "workTelephone": "{{workTelephone}}", "mobile": "{{mobile}}", "workEmail": "{{workEmail}}", "otherEmail": "{{otherEmail}}" } | Passed | Yes
OrangeHRM045 | Employee | User have token | Negative | User Double Hit EmployeeContact Detail but id not registered | User able to see error Employee not found | {{url}}/api/v1/employee/:id/contact-detail | Verify Responses displayed: "error": { "status": "404", "text": "Employee Not Found" } | Responses already displayed correctly: "error": { "status": "404", "text": "Employee Not Found" } | Passed | No
OrangeHRM046 | Employee | User have token | Positive | User Hit Query Save Employee Contact Detail | User able to save Employee Contact Detail | Hit Query {{url}}/api/v1/employee/:id/contact-detail | Verify Responses displayed: "data": { "id": "{{id}}", "code": "{{code}}", "fullName": "{{fullName}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "county": "{{county}}", "homeTelephone": "{{homeTelephone}}", "workTelephone": "{{workTelephone}}", "mobile": "{{mobile}}", "workEmail": "{{workEmail}}", "otherEmail": "{{otherEmail}}" } | Responses already displayed correctly: "data": { "id": "{{id}}", "code": "{{code}}", "fullName": "{{fullName}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "county": "{{county}}", "homeTelephone": "{{homeTelephone}}", "workTelephone": "{{workTelephone}}", "mobile": "{{mobile}}", "workEmail": "{{workEmail}}", "otherEmail": "{{otherEmail}}" } | Passed | Yes
OrangeHRM047 | Employee | User have token | Negative | User Hit Query Save Employee but zip is String | Zip cannot be string | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "qwerty", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "{{randommobile}}", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" } | Verify Responses displayed: "error": { "status": "202” "text": "Zip cannot be String” } | Tesponses already displayed correctly: "success": "{{successMessage}}", | Failed | No | Bug001
OrangeHRM048 | Employee | User have token | Negative | User Hit Query Save Employee but homeTelephone is Empty String | homeTelephone must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "", "workTelephone": "{{randomworkTelephone}}", "mobile": "{{randommobile}}", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "homeTelephone must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "homeTelephone must be a valid telephone number" } | Passed | No
OrangeHRM049 | Employee | User have token | Negative | User Hit Query Save Employee but homeTelephone is String | homeTelephone must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "string", "workTelephone": "{{randomworkTelephone}}", "mobile": "{{randommobile}}", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "homeTelephone must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "homeTelephone must be a valid telephone number" } | Passed | No
OrangeHRM050 | Employee | User have token | Negative | User Hit Query Save Employee but homeTelephone is Special Character | homeTelephone must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "^&$$$%$%&", "workTelephone": "{{randomworkTelephone}}", "mobile": "{{randommobile}}", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "homeTelephone must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "homeTelephone must be a valid telephone number" } | Passed | No
OrangeHRM051 | Employee | User have token | Negative | User Hit Query Save Employee but homeTelephone is Combination Other Chars and Alphabetic | workTelephone must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "testing", "mobile": "{{randommobile}}", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "workTelephone must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "workTelephone must be a valid telephone number" } | Passed | No
OrangeHRM052 | Employee | User have token | Negative | User Hit Query Save Employee but workTelephone is Empty String | workTelephone must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "", "mobile": "{{randommobile}}", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "workTelephone must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "workTelephone must be a valid telephone number" } | Passed | No
OrangeHRM053 | Employee | User have token | Negative | User Hit Query Save Employee but workTelephone is String | workTelephone must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "string", "mobile": "{{randommobile}}", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "workTelephone must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "workTelephone must be a valid telephone number" } | Passed | No
OrangeHRM054 | Employee | User have token | Negative | User Hit Query Save Employee but workTelephone is Special Character | workTelephone must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "$^%$%$%$", "mobile": "{{randommobile}}", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "workTelephone must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "workTelephone must be a valid telephone number" } | Passed | No
OrangeHRM055 | Employee | User have token | Negative | User Hit Query Save Employee but workTelephone is Combination Other Chars and Alphabetic | homeTelephone must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "testing123", "mobile": "{{randommobile}}", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "workTelephone must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "workTelephone must be a valid telephone number" } | Passed | No
OrangeHRM056 | Employee | User have token | Negative | User Hit Query Save Employee but mobile is Empty String | mobile must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "mobile must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "mobile must be a valid telephone number" } | Passed | No
OrangeHRM057 | Employee | User have token | Negative | User Hit Query Save Employee but mobile is String | mobile must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "string", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "mobile must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "mobile must be a valid telephone number" } | Passed | No
OrangeHRM058 | Employee | User have token | Negative | User Hit Query Save Employee but mobile is Special Character | mobile must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "$#$#$#$#", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "mobile must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "mobile must be a valid telephone number" } | Passed | No
OrangeHRM059 | Employee | User have token | Negative | User Hit Query Save Employee but mobile is Combination Other Chars and Alphabetic | mobile must be a valid telephone number | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "testing123", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "mobile must be a valid telephone number" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "mobile must be a valid telephone number" } | Passed | No
OrangeHRM060 | Employee | User have token | Negative | User Hit Query Save Employee but workEmail is Empty String | work Email must be valid email | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "{{randommobile}}, "workEmail": "", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "workEmail must be valid email" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "workEmail must be valid email" } | Passed | No
OrangeHRM061 | Employee | User have token | Negative | User Hit Query Save Employee but workEmail is Invalid FormatEmail | work Email must be valid email | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "{{randommobile}}, "workEmail": "testingemail", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "error": { "status": "202", "text": "workEmail must be valid email" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "workEmail must be valid email" } | Passed | No
OrangeHRM062 | Employee | User have token | Negative | User Hit Query Save Employee but otherEmail is Empty string | other Email must be valid email | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "{{randommobile}}, "workEmail": "{{randomWorkEmail}}", "otherEmail": "" | Verify Responses displayed: "error": { "status": "202", "text": "otherEmail must be valid email" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "otherEmail must be valid email" } | Passed | No
OrangeHRM063 | Employee | User have token | Negative | User Hit Query Save Employee but otherEmail is Invalid FormatEmail | other Email must be valid email | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "{{randommobile}}, "workEmail": "{{randomWorkEmail}}", "otherEmail": "testingemail" | Verify Responses displayed: "error": { "status": "202", "text": "otherEmail must be valid email" } | Tesponses already displayed correctly: "error": { "status": "202", "text": "otherEmail must be valid email" } | Passed | No
OrangeHRM064 | Employee | User have token | Negative | User Hit Query Save Employee but workEmail and otherEmail is same | Work Email And Other Email Cannot Be Same | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "{{randommobile}}, "workEmail": "testingemail@gmail.com", "otherEmail": "testingemail@gmail.com" | Verify Responses displayed: "error": [ "Work Email And Other Email Cannot Be Same" ] | Tesponses already displayed correctly: "error": [ "Work Email And Other Email Cannot Be Same" ] | Passed | No
OrangeHRM065 | Employee | User have token | Positive | User Hit Query Update Employee Contact Detail | User able to Update Employee Contact Detail | "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "{{zip}}", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "{{randommobile}}", "workEmail": "{{randomWorkEmail}}", "otherEmail": "{{randomOtherEmail}}" | Verify Responses displayed: "success": "{{successMessage}}", | Tesponses already displayed correctly: "success": "{{successMessage}}", | Passed | Yes
OrangeHRM066 | Employee | User have token | Positive | User Hit Query Save Employee Dependent | User able to save Employee Dependent | "id":"{{newemployeeid}}", "name":"{{nameDependent}}", "relationship":"{{relationship}}", "dob":"{{dobDependent}}" | Verify Responses displayed: "success": "{{successMessage}}", "sequenceNumber": "{{sequenceNumber}}" | Responses already displayed correctly: "success": "{{successMessage}}", "sequenceNumber": "{{sequenceNumber}}" | Passed | Yes
OrangeHRM067 | Employee | User have token | Positive | User Hit Query Get Employee Dependent | User able to Get Employee Dependent | Hit Query {{url}}/api/v1/employee/:id/dependent | Verify Responses displayed: "data": [ { "name": "{{name}}", "relationship": "{{relationship}}", "dob": "{{dob}}", "sequenceNumber": "{{sequenceNumber}}" } ] | Responses already displayed correctly: "data": [ { "name": "{{name}}", "relationship": "{{relationship}}", "dob": "{{dob}}", "sequenceNumber": "{{sequenceNumber}}" } ] | Passed | Yes
OrangeHRM068 | Employee | User have token | Positive | User Hit Query Delete Employee Dependent | User able to Delete Employee Dependent | "sequenceNumber":"{{sequenceNumber}}" | Verify Responses displayed: "success": "{{successDeleteMessage}}", | Verify Responses displayed: "success": "{{successDeleteMessage}}", | Passed | Yes
OrangeHRM069 | Employee | User have token | Positive | User Hit Query Terminate Employee | User able to Terminate Employee | "id": "{{newemployeeid}}", "date": "{{dateTerminate}}", "reason":"{{reason}}", "note": "{{note}}" | Verify Responses displayed: "success": "{{successMessage}}", | Tesponses already displayed correctly: "success": "{{successMessage}}", | Passed | Yes
[9 empty] | Total Scenario | 69
[9 empty] | Total Scenario Passed | 68
[9 empty] | Total Scenario Failed | 1
[9 empty] | Total Scenario Automated | 16
[9 empty] | Total Scenario Running Manual | 53
[9 empty] | Total Scenario Positive | 16
[9 empty] | Total Scenario Negative | 53

## UAT Report (hidden)
Two Wheelers EFP
- Project Information - |  | - Test Result - |  |  |  | - Execution Plan - |  | - Actual Execution -
Report Date. | 2021-09-28 | Status. | OK |  |  | Start Date. | 0 | Start Date. | 0
Project No. | UAT | Completion. | 100% Tested Correctly / 100% Executed |  |  | Finish Date. | 0 | Finish Date. | 0
Test Env. | C1 | Total Test Case. | 55
- Total Results To Date -
Status. | Planned #. | Planned % | Actual #. | Actual % from Result to Date.
Plan. | 64 | 100% | 64 | 100%
Tested correctly | 64 | 100% | 64 | 100%
Tested with non Stopping Defect |  |  | 0 | 0%
Tested with Showstopper |  |  | 0 | 0%
In Progress |  |  | 0 | 0%
N/A |  |  | 0 | 0%
Not Tested |  |  | 0 | 0%
- Defect / Issue Details -
Defect ID (#) | Defect Name | Description |  | PIC | Status | Detected Date | Closed Date | Type | Blocked Test Case
Bug001 | Zip able to input String | Normal |  | Responses already displayed correctly: "error": { "status": "202” "text": "Zip cannot be String” } | Open | 2021-09-27 | 0 | ISSUE | 0
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
No. | Type. | Scenario ID | Scenario Case |  |  |  |  | Result.
1 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
2 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
3 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
4 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
5 | Positive | User Hit Query Save Employee Detail but lastName empty string | #VALUE! |  |  |  |  | Tested Correctly
6 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
7 | #VALUE! | User Hit Query Save Employee but code is empty | #VALUE! |  |  |  |  | #VALUE!
8 | Positive | #VALUE! | User Hit Query Get Employee Detail but id not registered |  |  |  |  | Tested Correctly
9 | #REF! | User Hit Query Save Employee but code more than 10 int | #VALUE! |  |  |  |  | #REF!
10 | #REF! | User Hit Query Save Employee but firstName is Integer | #VALUE! |  |  |  |  | #REF!
11 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
12 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
13 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!
14 | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | #VALUE!

## SIT Scenario (hidden)
No | Scenario ID | Scenario Cases | Product Code | Involved System or Application | Pre Condition | Scenario Type | Planned Date | Execution Date | Status | Tester | Notes

## Reff Table (hidden)
Test Cycle | Test Env | Progress / Result | Test Priority | Scenario Type | Status | Defect / Issue | Defect Status
SIT | C1 | OK | High | Positive | Tested correctly | DEFECT | Open
| PreProd | OK | High | Positive | Tested correctly | DEFECT | Open
UAT | C2 | NOT OK | Medium | Negative | Tested with non Stopping Defect | ISSUE | In Progress
| C3 | In Progress | Low | Regression | Not Tested |  | Closed
| PreProd |  | Critical |  | N/A
| Production |  |  |  | In Progress
Tested with Showstopper

## Findings
Jira ID (#) | Title | Priority | Step to Reproduce | Expected Result | Actual Result | PIC | Status | Detected Date | Closed Date | Type | Blocked Test Case | Remarks
Bug001 | Zip able to input String | Normal | Hit Query {{url}}/api/v1/employee/:id/contact-detail { "id": "{{NewEmployeeId}}", "addressStreet1": "{{addressStreet1}}", "addressStreet2": "{{addressStreet2}}", "city": "{{city}}", "state": "{{state}}", "zip": "qwerty", "country": "{{country}}", "homeTelephone": "{{randomhomeTelephone}}", "workTelephone": "{{randomworkTelephone}}", "mobile": "{{randommobile}}", "workEmail": "{{randomWorkEmail}}", “otherEmail": "{{randomOtherEmail}}" }”” | Responses already displayed correctly: "error": { "status": "202” "text": "Zip cannot be String” } | Tesponses already displayed correctly: "success": "{{successMessage}}", | Arisa | Open | 2021-09-27 |  | ISSUE